Batch-Mode Schedule Optimization

with Disjunctive Graphs and Tabu Search

Complete Design Specification

CTP Scheduling Platform  —  April 2026

Target: 1000-task manufacturing landscape

Overnight / 2–3x daily batch optimization runs

# 1. Overview and Architecture

This document specifies the complete design for batch-mode schedule optimization — a background process that takes an existing schedule produced by the AbA constructive solver, represents it as a disjunctive graph, and systematically improves it using tabu search and iterated local search (ILS). The optimizer runs overnight or 2–3 times per day, producing a proposed improved schedule that planners review and accept or reject.

The optimizer is not a replacement for the AbA engine. It is a post-processing layer that sits on top of the existing solver. The AbA engine remains the interactive tool for real-time scheduling — what-if scenarios, WhereTo moves, single-task scheduling. The optimizer is the “second opinion” that finds global improvements the constructive solver cannot see.

## Architecture Layers

┌─────────────────────────────────────────────────┐ │ Layer 1: API │ │ POST /v1/ctp/optimize → kick off job │ │ GET /v1/ctp/optimize/:jobId → poll status │ │ POST /v1/ctp/optimize/:jobId/accept → commit │ │ POST /v1/ctp/optimize/:jobId/reject → discard │ └──────────────────┬──────────────────────────────┘ │ ┌──────────────────▼──────────────────────────────┘ │ Layer 2: Job Orchestration │ │ Redis/Service Bus queue, progress tracking, │ │ landscape snapshot, timeout, cancellation │ └──────────────────┬──────────────────────────────┘ │ ┌──────────────────▼──────────────────────────────┘ │ Layer 3: Optimization Engine │ │ DisjunctiveGraph → CriticalPath → TabuSearch │ │ → ILS multi-pass → DiffCompute → Result │ └─────────────────────────────────────────────────┘

# 2. Data Structures

The optimizer uses its own data structures optimized for fast neighborhood exploration. These are built from the existing SchedulingLandscape after a constructive solve and are independent of the engine’s internal models.

## 2.1 DisjunctiveGraph

The graph uses integer-indexed flat arrays rather than object references. This is deliberate: neighborhood moves need to swap edges efficiently, and index-based adjacency is faster to serialize, clone, and diff than linked object graphs.

### GraphNode

Each node represents one scheduled task. The graph contains one node per scheduled task plus two sentinel nodes (source and sink).

interface GraphNode { index: number; // Integer ID (0..N+1) taskKey: string; // Maps back to CTPTask.key resourceKey: string; // Primary resource assigned allResourceKeys: string[]; // All resources (multi-resource) orderKey: string ¦ null; // linkId.name (order reference) processStep: number; // Sequence within the order chain // Timing (seconds since epoch, matching CTPInterval.startW) duration: number; // Task duration in seconds scheduledStart: number; // From current AbA solve scheduledEnd: number; // From current AbA solve // Changeover context subType: string ¦ null; // Product/process type for changeover changeoverBefore: number; // Changeover duration before this task // Edges (stored as arrays of node indices) conjPredecessors: number[]; // Hard precedence: chain links conjSuccessors: number[]; // Hard precedence: chain links disjPredecessors: number[]; // Resource sequencing (can be swapped) disjSuccessors: number[]; // Resource sequencing (can be swapped) // Critical path fields (computed by forward/backward pass) earliestStart: number; // Forward pass result earliestEnd: number; // earliestStart + duration latestStart: number; // Backward pass result latestEnd: number; // latestStart + duration totalSlack: number; // latestStart - earliestStart isOnCriticalPath: boolean; // totalSlack === 0 criticalBlockId: number; // Which critical block (-1 if none) // Freeze control isFrozen: boolean; // Cannot be moved by optimizer isPinned: boolean; // Pinned in current landscape }

### DisjunctiveGraph

The graph container holds all nodes and provides the operations needed for construction, critical path computation, and neighborhood moves.

class DisjunctiveGraph { nodes: GraphNode[]; // Flat array, index-addressable sourceIndex: number; // Virtual start node (index 0) sinkIndex: number; // Virtual end node (index N+1) taskKeyToIndex: Map<string, number>; // Reverse lookup // Per-resource task ordering (resource key -> node indices in time order) resourceSequences: Map<string, number[]>; // Critical path state criticalPath: number[]; // Ordered node indices on critical path criticalBlocks: CriticalBlock[]; makespan: number; // Length of critical path // Construction static fromLandscape(landscape: SchedulingLandscape, freezeHorizon?: number): DisjunctiveGraph; // Critical path computeCriticalPath(): void; // Forward + backward pass O(T+E) identifyCriticalBlocks(): void; // Neighborhood operations swapOnResource(resourceKey: string, nodeA: number, nodeB: number): SwapResult; reverseSwap(swap: SwapResult): void; clone(): DisjunctiveGraph; // For snapshot/restore // Translation back to engine toLandscape(originalLandscape: SchedulingLandscape ): SchedulingLandscape; computeDiff(original: DisjunctiveGraph): TaskDiff[]; }

### CriticalBlock

A critical block is a maximal sequence of consecutive critical-path tasks on the same resource. Only swaps at the boundaries of critical blocks can improve the makespan — this is the Taillard insight that makes neighborhood search efficient.

interface CriticalBlock { id: number; resourceKey: string; nodeIndices: number[]; // Tasks in this block (time-ordered) firstIndex: number; // First task in the block lastIndex: number; // Last task in the block totalDuration: number; // Sum of task durations in block percentOfMakespan: number; // How much of critical path this owns }

### Mapping to Existing Engine Models

The graph is built from the solved landscape. Here is exactly how each engine concept maps to a graph element:

| Engine Model | Graph Element | Source Field |
| --- | --- | --- |
| CTPTask (scheduled) | GraphNode | task.key, task.scheduled.startW/endW |
| CTPTask.linkId.prevLink | Conjunctive arc (predecessor) | chain relationship |
| Two tasks on same resource | Disjunctive arc (sequencing) | resource.assignments order |
| CTPTask.capacityResources[] | node.allResourceKeys[] | all assigned resources |
| CTPStateChange (changeover) | node.changeoverBefore | stateChanges lookup |
| CTPTask.pinned = true | node.isPinned = true | immutable in optimizer |
| CTPTask.wipstate = IN_PROCESS | node.isFrozen = true | cannot be moved |
| ScheduleContext | Arc orientation (who goes first) | resource sequence order |
| Blended score (ScoringEngine) | Objective function on critical path | scoring rules config |

# 3. Graph Construction (fromLandscape)

Graph construction transforms a solved SchedulingLandscape into the integer-indexed DisjunctiveGraph. This runs once at the start of each optimization job.

## Step-by-Step Algorithm

1. Create source node (index 0) and sink node (index N+1). Source has duration 0, start at horizon start. Sink has duration 0, start at horizon end.

2. Walk landscape.tasks. For each task where task.state === SCHEDULED, create a GraphNode. Assign sequential integer indices (1..N). Populate taskKey, duration (task.scheduled.endW - task.scheduled.startW), scheduledStart, scheduledEnd, and all resource keys from task.capacityResources[].scheduledResource.

3. Build conjunctive arcs from chain relationships. Walk landscape.processes. For each CTPProcess, iterate its sorted task list. For consecutive tasks A and B in the same process, add a conjunctive edge: A.conjSuccessors.push(B.index), B.conjPredecessors.push(A.index). These edges are immutable during optimization.

4. Build disjunctive arcs from resource sequencing. For each resource in landscape.resources, collect all GraphNodes assigned to that resource (using node.allResourceKeys). Sort them by scheduledStart. For consecutive tasks A and B in this resource sequence, add a disjunctive edge: A.disjSuccessors.push(B.index), B.disjPredecessors.push(A.index). Store the sequence in resourceSequences.set(resourceKey, [nodeIndices]).

5. Connect source and sink. Source gets a conjunctive edge to every node with no predecessors (conjunctive or disjunctive). Sink gets a conjunctive edge from every node with no successors. This ensures a single connected graph.

6. Compute changeovers. For each disjunctive edge A → B on a resource, look up the CTPStateChange between A.subType and B.subType using landscape.stateChanges.getOrDefaultProcessChange(). Store the duration on B.changeoverBefore.

7. Apply freeze horizon. For each node where scheduledStart < freezeHorizon or isPinned or wipstate !== NOT_STARTED, set isFrozen = true. Frozen nodes’ disjunctive arcs cannot be reversed during search.

## Multi-Resource Handling

Classic job shop graphs assume one resource per task. Your manufacturing tasks can require multiple resources simultaneously (e.g., a CNC machine + an operator). The graph handles this by creating disjunctive arcs on every resource a task uses. If task T uses resources R1 and R2, it appears in both resourceSequences[R1] and resourceSequences[R2], creating disjunctive edges on both timelines.

When evaluating a swap, the critical path computation naturally handles this — a task’s earliest start is constrained by the latest-finishing predecessor across all its resource timelines plus its chain predecessors. No special-case logic needed.

## Performance at 1000 Tasks

With 1000 tasks across ~30 resources: ~1000 nodes, ~1000 conjunctive arcs (chain links), ~3000–5000 disjunctive arcs (resource sequencing pairs). Graph construction is O(T + E) where T is tasks and E is edges. At this scale, construction completes in under 10ms.

# 4. Critical Path Computation

The critical path is the longest weighted path from source to sink. It determines the makespan. Every task on the critical path has zero slack — if any of them slips, the makespan increases. Tasks not on the critical path can shift without affecting the schedule length.

## 4.1 Forward Pass

Process nodes in topological order (guaranteed acyclic because the schedule is feasible). For each node, compute the earliest possible start time:

forwardPass() { // Topological sort (Kahn's algorithm) const inDegree = new Int32Array(this.nodes.length); for (const node of this.nodes) { for (const pred of node.conjPredecessors) inDegree[node.index]++; for (const pred of node.disjPredecessors) inDegree[node.index]++; } const queue: number[] = []; for (const node of this.nodes) { if (inDegree[node.index] === 0) queue.push(node.index); } while (queue.length > 0) { const idx = queue.shift()!; const node = this.nodes[idx]; // Earliest start = max of all predecessors' earliest end + changeover let maxPredEnd = 0; for (const pred of [...node.conjPredecessors, ...node.disjPredecessors]) { const predEnd = this.nodes[pred].earliestEnd; maxPredEnd = Math.max(maxPredEnd, predEnd); } node.earliestStart = maxPredEnd + node.changeoverBefore; node.earliestEnd = node.earliestStart + node.duration; // Decrement successors' in-degree for (const succ of [...node.conjSuccessors, ...node.disjSuccessors]) { if (--inDegree[succ] === 0) queue.push(succ); } } this.makespan = this.nodes[this.sinkIndex].earliestStart; }

## 4.2 Backward Pass

Process nodes in reverse topological order. For each node, compute the latest allowable start time:

backwardPass() { this.nodes[this.sinkIndex].latestStart = this.makespan; this.nodes[this.sinkIndex].latestEnd = this.makespan; // Reverse topological order for (const node of reverseTopoOrder) { let minSuccStart = this.makespan; for (const succ of [...node.conjSuccessors, ...node.disjSuccessors]) { const succStart = this.nodes[succ].latestStart - this.nodes[succ].changeoverBefore; minSuccStart = Math.min(minSuccStart, succStart); } node.latestEnd = minSuccStart; node.latestStart = node.latestEnd - node.duration; node.totalSlack = node.latestStart - node.earliestStart; node.isOnCriticalPath = (node.totalSlack === 0); } }

## 4.3 Critical Block Identification

After the forward and backward passes, walk each resource sequence and group consecutive critical-path tasks into blocks:

identifyCriticalBlocks() { this.criticalBlocks = []; let blockId = 0; for (const [resourceKey, sequence] of this.resourceSequences) { let currentBlock: number[] = []; for (const nodeIdx of sequence) { const node = this.nodes[nodeIdx]; if (node.isOnCriticalPath) { currentBlock.push(nodeIdx); } else { if (currentBlock.length >= 2) { this.criticalBlocks.push({ id: blockId++, resourceKey, nodeIndices: [...currentBlock], firstIndex: currentBlock[0], lastIndex: currentBlock[currentBlock.length - 1], totalDuration: currentBlock.reduce( (s, i) => s + this.nodes[i].duration, 0), percentOfMakespan: 0, // computed after }); currentBlock.forEach( i => this.nodes[i].criticalBlockId = blockId - 1); } currentBlock = []; } } // Flush last block if (currentBlock.length >= 2) { this.criticalBlocks.push({ id: blockId++, resourceKey, nodeIndices: [...currentBlock], firstIndex: currentBlock[0], lastIndex: currentBlock[currentBlock.length - 1], totalDuration: currentBlock.reduce( (s, i) => s + this.nodes[i].duration, 0), percentOfMakespan: 0, }); currentBlock.forEach( i => this.nodes[i].criticalBlockId = blockId - 1); } } // Compute percentages for (const block of this.criticalBlocks) { block.percentOfMakespan = (block.totalDuration / this.makespan) * 100; } }

At 1000 tasks, the full critical path computation (forward pass + backward pass + block identification) takes 2–5ms. This runs once per tabu search iteration, so 3000 iterations adds ~10–15 seconds. Well within the overnight budget.

# 5. Tabu Search Algorithm

Tabu search is the core improvement engine. It explores the neighborhood of the current solution by swapping task pairs on critical-path resource sequences, using a short-term memory (the tabu list) to prevent cycling.

## 5.1 Neighborhood Definition

The neighborhood is defined by critical-path swaps. Only swaps involving critical-path tasks can improve the makespan. The Taillard N7 neighborhood specifically targets the boundaries of critical blocks:

interface NeighborhoodMove { resourceKey: string; nodeA: number; // First task in swap nodeB: number; // Second task in swap blockId: number; // Which critical block moveType: 'boundary_first' ¦ 'boundary_last' ¦ 'internal'; }

For each critical block, generate candidate moves:

1. Swap the first task in the block with its resource predecessor (from outside the block or from the previous block). This pulls a task into the block earlier.

2. Swap the last task in the block with its resource successor (from outside the block or from the next block). This pushes a task out of the block later.

3. Optional: swap internal adjacent pairs within the block. These are less likely to improve makespan but can help in multi-resource scenarios.

At 1000 tasks with 8–15 critical blocks averaging 5–12 tasks each, the neighborhood per iteration is 20–60 candidate moves. This is small enough to evaluate exhaustively.

## 5.2 Move Evaluation

For each candidate move, tentatively apply the swap and recompute the critical path:

evaluateMove(move: NeighborhoodMove): MoveEvaluation { const { resourceKey, nodeA, nodeB } = move; // 1. Check freeze constraints if (this.nodes[nodeA].isFrozen ¦¦ this.nodes[nodeB].isFrozen) return { feasible: false, newMakespan: Infinity }; // 2. Tentatively swap the disjunctive arc this.swapOnResource(resourceKey, nodeA, nodeB); // 3. Recompute changeovers for affected tasks this.recomputeChangeovers(resourceKey, nodeA, nodeB); // 4. Check feasibility (no cycles introduced) if (this.hasCycle()) { this.reverseSwap(move); return { feasible: false, newMakespan: Infinity }; } // 5. Recompute critical path this.computeCriticalPath(); const newMakespan = this.makespan; // 6. Reverse the swap (we're just evaluating) this.reverseSwap(move); this.computeCriticalPath(); // Restore original state return { feasible: true, newMakespan }; }

## 5.3 The Swap Operation

Swapping two adjacent tasks on a resource means reversing their disjunctive arc and updating the resource sequence:

swapOnResource(resourceKey: string, nodeA: number, nodeB: number): SwapResult { // nodeA is currently before nodeB on this resource // 1. Remove A -> B disjunctive edge remove(this.nodes[nodeA].disjSuccessors, nodeB); remove(this.nodes[nodeB].disjPredecessors, nodeA); // 2. Add B -> A disjunctive edge (reversed) this.nodes[nodeB].disjSuccessors.push(nodeA); this.nodes[nodeA].disjPredecessors.push(nodeB); // 3. Update resource sequence const seq = this.resourceSequences.get(resourceKey)!; const idxA = seq.indexOf(nodeA); const idxB = seq.indexOf(nodeB); seq[idxA] = nodeB; seq[idxB] = nodeA; // 4. Update neighbor edges (predecessor of A and successor of B) // reconnect the chain around the swapped pair this.reconnectNeighbors(resourceKey, nodeA, nodeB); return { resourceKey, nodeA, nodeB, reversed: true }; }

## 5.4 The Tabu List

The tabu list prevents cycling by remembering recently reversed moves. Each entry records a swap (nodeA, nodeB, resourceKey). A move is “tabu” if its reverse is on the list. The list has a fixed size (tabu tenure); when full, the oldest entry is removed.

interface TabuEntry { nodeA: number; nodeB: number; resourceKey: string; iteration: number; // When this entry was added } class TabuList { entries: TabuEntry[] = []; tenure: number; // Max size (15-25 for 1000 tasks) isTabu(move: NeighborhoodMove, currentIter: number): boolean { return this.entries.some(e => e.nodeA === move.nodeB && e.nodeB === move.nodeA && e.resourceKey === move.resourceKey && (currentIter - e.iteration) < this.tenure ); } add(move: NeighborhoodMove, iteration: number): void { this.entries.push({ nodeA: move.nodeA, nodeB: move.nodeB, resourceKey: move.resourceKey, iteration }); if (this.entries.length > this.tenure * 2) this.entries = this.entries.slice(-this.tenure); } }

Aspiration criterion: a tabu move is accepted anyway if it produces a new global best makespan. This prevents the tabu list from blocking clearly beneficial moves.

## 5.5 Main Tabu Search Loop

tabuSearch(graph: DisjunctiveGraph, config: TabuConfig) : TabuSearchResult { const tabu = new TabuList(config.tenure); // 15-25 let bestMakespan = graph.makespan; let bestSnapshot = graph.clone(); let noImproveCount = 0; for (let iter = 0; iter < config.maxIterations; iter++) { // 1. Identify critical path and blocks graph.computeCriticalPath(); graph.identifyCriticalBlocks(); // 2. Generate neighborhood moves const moves = generateNeighborhood(graph); // 3. Evaluate all candidate moves let bestMove: NeighborhoodMove ¦ null = null; let bestMoveMakespan = Infinity; for (const move of moves) { const eval = graph.evaluateMove(move); if (!eval.feasible) continue; const isTabu = tabu.isTabu(move, iter); const aspirationMet = eval.newMakespan < bestMakespan; if (!isTabu ¦¦ aspirationMet) { if (eval.newMakespan < bestMoveMakespan) { bestMoveMakespan = eval.newMakespan; bestMove = move; } } } // 4. Apply best move (even if it worsens current solution) if (bestMove) { graph.swapOnResource(bestMove.resourceKey, bestMove.nodeA, bestMove.nodeB); graph.recomputeChangeovers(bestMove.resourceKey, bestMove.nodeA, bestMove.nodeB); tabu.add(bestMove, iter); graph.computeCriticalPath(); // 5. Track global best if (graph.makespan < bestMakespan) { bestMakespan = graph.makespan; bestSnapshot = graph.clone(); noImproveCount = 0; } else { noImproveCount++; } } else { noImproveCount++; } // 6. Early termination if stuck if (noImproveCount > config.stagnationLimit) break; // 7. Report progress periodically if (iter % 100 === 0) { reportProgress(iter, config.maxIterations, bestMakespan); } } return { bestGraph: bestSnapshot, bestMakespan, iterations: iter }; }

# 6. Iterated Local Search (ILS)

ILS extends tabu search by running multiple passes from different starting points. After each tabu search converges (hits the stagnation limit), the solution is perturbed and search restarts. This explores a broader region of the solution space.

## 6.1 Perturbation Strategy

The perturbation randomly rearranges 5–10% of the disjunctive arcs. This is enough to escape the local optimum without destroying the overall schedule structure:

perturb(graph: DisjunctiveGraph, strength: number): void { // strength = fraction of arcs to randomize (0.05 to 0.10) const allDisjArcs: [string, number, number][] = []; for (const [resKey, seq] of graph.resourceSequences) { for (let i = 0; i < seq.length - 1; i++) { if (!graph.nodes[seq[i]].isFrozen && !graph.nodes[seq[i+1]].isFrozen) { allDisjArcs.push([resKey, seq[i], seq[i+1]]); } } } // Randomly select arcs to reverse const count = Math.ceil(allDisjArcs.length * strength); const shuffled = allDisjArcs.sort(() => Math.random() - 0.5); for (let i = 0; i < count; i++) { const [resKey, nodeA, nodeB] = shuffled[i]; graph.swapOnResource(resKey, nodeA, nodeB); } // Recompute all changeovers and critical path graph.recomputeAllChangeovers(); graph.computeCriticalPath(); }

## 6.2 ILS Main Loop

iteratedLocalSearch(landscape: SchedulingLandscape, config: ILSConfig): OptimizationResult { const graph = DisjunctiveGraph.fromLandscape( landscape, config.freezeHorizon); graph.computeCriticalPath(); const originalMakespan = graph.makespan; let globalBest = graph.clone(); let globalBestMakespan = graph.makespan; const passResults: PassResult[] = []; for (let pass = 0; pass < config.passes; pass++) { // Perturb (except first pass - use constructive solution) if (pass > 0) { perturb(graph, config.perturbStrength); } // Run tabu search const result = tabuSearch(graph, { tenure: config.tabuTenure, // 15-25 maxIterations: config.iterationsPerPass, // 1000-3000 stagnationLimit: config.stagnationLimit, // 200-500 }); passResults.push({ pass: pass + 1, makespan: result.bestMakespan, improvement: ((originalMakespan - result.bestMakespan) / originalMakespan) * 100, iterations: result.iterations, }); if (result.bestMakespan < globalBestMakespan) { globalBestMakespan = result.bestMakespan; globalBest = result.bestGraph; } // Check time budget if (elapsed() > config.timeBudgetMs) break; } // Compute diff between original and best const originalGraph = DisjunctiveGraph.fromLandscape(landscape); const diff = globalBest.computeDiff(originalGraph); return { originalMakespan, optimizedMakespan: globalBestMakespan, improvementPercent: ((originalMakespan-globalBestMakespan)/originalMakespan)*100, passResults, diff, optimizedGraph: globalBest, }; }

# 7. Translating Back to the Landscape

After the optimizer finds an improved solution in graph space, it must be translated back into the engine’s SchedulingLandscape so that the planner can review and accept it.

## 7.1 toLandscape Algorithm

1. Clone the original landscape (deep copy of tasks, resources, processes).

2. Unschedule all non-frozen tasks using the existing ScheduleEngine.unschedule() method. This restores resource availability.

3. Read the optimized graph’s resource sequences. For each resource, iterate through the node ordering from the graph. For each node, use the graph’s earliestStart as the target start time.

4. Schedule each task using the existing ScheduleEngine.schedule() method, passing a BestScheduleContext built from the graph node’s resource assignments and computed start time. Process in topological order to respect precedence.

5. Validate: confirm every task that was scheduled in the original is still scheduled. If any task becomes infeasible (calendar gaps, constraint violations the graph abstraction missed), flag it and report.

The translation step uses the EXISTING ScheduleEngine.schedule() and ScheduleEngine.unschedule() methods. The optimizer never manipulates resource availability directly — it delegates to the proven engine code. This ensures changeovers, calendar constraints, and material interactions are correctly handled.

## 7.2 Diff Computation

The diff compares the original and optimized schedules task by task:

interface TaskDiff { taskKey: string; taskName: string; orderKey: string ¦ null; changeType: 'moved' ¦ 'resource_changed' ¦ 'both' ¦ 'unchanged'; original: { start: string; // ISO date end: string; resourceKey: string; }; optimized: { start: string; end: string; resourceKey: string; }; startDeltaSeconds: number; // Positive = moved later makespanImpact: number; // How much this move contributed reason: string; // 'Moved off critical path bottleneck' }

# 8. API Design

## 8.1 POST /v1/ctp/optimize

Kicks off a background optimization job. Returns immediately.

// Request { "timeBudgetSeconds": 300, "objective": "makespan", "passes": 5, "tabuTenure": 20, "iterationsPerPass": 2000, "perturbStrength": 0.07, "constraints": { "freezeHorizon": "2026-04-04T06:00:00Z", "pinnedTasks": ["TASK-001"], "lockedOrders": ["ORD-005"] } } // Response (immediate) { "jobId": "opt-20260403-001", "status": "queued", "startedAt": "2026-04-03T22:00:00Z", "estimatedSeconds": 300 }

## 8.2 GET /v1/ctp/optimize/:jobId

Poll for status and results. Returns progress while running, full results when complete.

// While running { "status": "running", "progress": { "currentPass": 3, "totalPasses": 5, "iterationsThisPass": 847, "bestMakespanSoFar": 432000, "improvementPercent": 12.3, "elapsedSeconds": 168 } } // When complete { "status": "complete", "result": { "originalMakespan": 493200, "optimizedMakespan": 432000, "improvementPercent": 12.4, "tasksMoved": 47, "tasksUnchanged": 953, "passResults": [ ... ], "criticalPath": { ... }, "diff": [ ... ] // Array of TaskDiff } }

## 8.3 POST /v1/ctp/optimize/:jobId/accept

Planner accepts the optimized schedule. The optimized landscape replaces the current state.

## 8.4 POST /v1/ctp/optimize/:jobId/reject

Planner rejects the optimization. The original schedule remains untouched. Job results are archived for analytics.

# 9. Configuration Parameters

These parameters control the optimizer’s behavior. Defaults are tuned for a 1000-task manufacturing landscape with a 5-minute time budget.

| Parameter | Default | Range | Description |
| --- | --- | --- | --- |
| timeBudgetSeconds | 300 | 30–600 | Total wall clock time budget for the optimization job |
| passes | 5 | 1–10 | Number of ILS restart passes |
| iterationsPerPass | 2000 | 500–5000 | Maximum tabu search iterations per pass |
| tabuTenure | 20 | 10–30 | Number of iterations a move stays tabu. Scale with sqrt(tasks) |
| stagnationLimit | 300 | 100–500 | Stop tabu pass after this many iterations without improvement |
| perturbStrength | 0.07 | 0.03–0.15 | Fraction of disjunctive arcs to randomize between ILS passes |
| freezeHorizon | null | ISO date | Tasks starting before this time cannot be moved |
| objective | makespan | — | Primary metric to optimize. Future: weighted blend |
| Tabu tenure recommendation: sqrt(number of tasks). For 1000 tasks, tenure = ~31, rounded down to 20–25 for conservatism. Too short = cycling. Too long = restricted exploration. |  |  |  |

# 10. Performance Estimates at 1000 Tasks

| Operation | Time | Notes |
| --- | --- | --- |
| Graph construction | 5–10ms | O(T+E), one-time |
| Critical path computation | 2–5ms | O(T+E), once per iteration |
| Neighborhood generation | <1ms | Scan critical blocks |
| Move evaluation (single) | 3–7ms | Swap + critical path + restore |
| Full iteration (40 moves) | 120–280ms | Evaluate all + apply best |
| One tabu pass (2000 iter) | 4–9 min | May terminate early at stagnation |
| Five ILS passes | 5–15 min | Depends on time budget cutoff |
| Translation back to landscape | 100–500ms | Unschedule + reschedule all moved tasks |
| Diff computation | <10ms | Compare two snapshots |

For overnight runs, a 15-minute time budget with 5–8 ILS passes is recommended. For mid-day runs (2–3x daily), a 3–5 minute budget with 2–3 passes provides a good balance.

# 11. Changeover Handling

Changeovers are a critical complication for manufacturing scheduling. When two tasks on the same resource have different product types (subType), the state change lookup determines the changeover duration. The optimizer must recompute changeovers whenever it swaps two tasks on a resource.

## 11.1 Recomputing After a Swap

When tasks A and B are swapped on a resource (B now goes before A), four changeovers may change:

1. The changeover before B (from B’s new predecessor to B)

2. The changeover before A (from B to A, since B now precedes A)

3. The changeover before A’s successor (from A to A’s new successor)

4. The changeover before B’s old predecessor’s successor (if different from B)

Each of these is computed by looking up the CTPStateChange for the resource type and the from/to subType pair, using the existing getOrDefaultProcessChange() method on the landscape’s stateChanges hash map. The changeover duration is stored on the affected node’s changeoverBefore field and included in the critical path computation (it adds to the effective duration between tasks).

Changeover-aware evaluation is what makes this optimizer respect real manufacturing constraints. A swap that looks good for makespan but introduces a 2-hour changeover where there was a 10-minute one will correctly show as a worse move.

# 12. Future Extensions

## Multi-Objective Optimization

The initial implementation optimizes makespan only. Future versions can extend the move evaluation to a weighted blend matching the tenant’s scoring configuration: makespan + on-time delivery + utilization balance + changeover minimization. The neighborhood generation (critical-path focus) still applies — the evaluation function becomes richer.

## Resource Reassignment

The current design only swaps task sequencing on fixed resource assignments. A future extension could also explore alternative resource assignments — moving a task from CNC-01 to CNC-03 if both are capable. This would add a second dimension to the neighborhood (sequencing moves + assignment moves) and leverage the existing CombinationEngine to enumerate alternatives.

## Machine Learning on Parameters

Over time, the optimizer’s parameters (tabu tenure, perturbation strength, iteration budget) can be tuned per-tenant based on historical optimization runs. Track which parameter settings produced the best improvements for each tenant’s data profile, and auto-suggest optimal settings. This connects directly to Willoughby’s vision of adaptive, self-tuning scheduling.

## Incremental Graph Updates

When a swap only affects two tasks on one resource, the full critical path recomputation (O(T+E)) could be replaced with a local update that only recomputes affected subgraph nodes. At 1000 tasks this optimization is not needed, but at 5000+ tasks it would reduce per-iteration time from milliseconds to microseconds.

CTP Scheduling Platform — April 2026